Refurbishment construction phase plan

Worked example of a made-up job. Not a plan for a real site.

| Rev | Date | What changed | By |
| --- | --- | --- | --- |
| 0 | 19 December 2025 | First issue | Dan Hollins |
| 1 | 7 January 2026 | Cabins moved to the rear yard. Deliveries by the rear doors | Dan Hollins |
| 2 | 9 February 2026 | Rear doors repaired one leaf at a time 10 to 13 February, so the exit stays open: board deliveries held to 16 February | Dan Hollins |

# The project

| Company | Hollins & Reed Contracting Ltd |
| --- | --- |
| Client | Thornley Vale Estates Ltd |
| Site address | Unit 7, Tanhouse Retail Park, Stockport |
| Description of the work | Strip-out of a vacant, stand-alone, single-storey shop to the landlord’s shell, then fit-out with new services. Scheduled: 55 working days, 14 people at most, 560 person days. |
| Principal designer | Greave Street Architects Ltd, appointed in writing 3 November 2025 |
| Principal contractor | Hollins & Reed Contracting Ltd, appointed in writing 24 November 2025 |
| Other key team members | Site manager: Dan Hollins, 0161 496 0142. Assistant: Priya Shah. Client’s agent: Owen Tattersall, 0161 496 0188. |
| Key dates | Start 12 January 2026. Strip-out done 30 January. First fix done 27 February. Handover 27 March 2026. |
| Notified to HSE | Yes, 15 December 2025. Notice on the site office wall. |

# Health and safety aims

What this project aims for.

Nobody on the job is hurt or made ill by the work. Nobody from the car park gets onto the site. Anyone on site can stop work they think is unsafe, and will be backed for it.

# Site rules

Protective equipment, parking, radios and phones, smoking, restricted areas, hot works.

Nobody works until inducted and signed in. Boots and hi-vis on site; eye protection, gloves and masks as your RAMS says. Park in the rear yard. Keep the gates shut. Radios off. No phones on a tower or steps. No smoking or vaping on site. Nobody goes on the roof. Hot works only on a permit from Dan Hollins.

# Contractors and specialists

| Company | Trade | Contact | Start |
| --- | --- | --- | --- |
| Brinnington Soft Strip Ltd | Strip-out | Lee Bramhall, 0161 496 0151 | 12 January |
| Davenport Rise Electrical Ltd | Lighting and power | Callum Whittle, 0161 496 0152 | 12 January |
| Tanyard Air Ltd | Heating and ventilation | K Tunnicliffe, 0161 496 0153 | 19 January |
| Offerton Interiors Ltd | Partitions, ceilings, floors, decorating | Mark Etchells, 0161 496 0154 | 2 February |

# Working together

How contractors cooperate and coordinate, regular site meetings, and how workers are involved.

Site meeting for all contractors every Monday at 08:00, chaired by Dan Hollins. Handover at 16:30 each day: who is where tomorrow. Each contractor gives Dan Hollins its RAMS before starting, and he checks it against the work around it. Workers raise anything at the Monday meeting or with their foreman, and a note of what was done goes up on the site board in the office.

# Site induction

Specific to this site: the particular risks here and how they are controlled.

Given by Dan Hollins or Priya Shah before anyone starts. It covers the job, who runs it, first aid, reporting accidents, daily talks, how to raise a concern, the exits, the fire points, dust and the permit for hot works. Visitors get a short version and stay with an escort.

# Induction record

| Name | Company | Date | Signed |
| --- | --- | --- | --- |
| Dan Hollins | Hollins & Reed Contracting Ltd | 12 Jan 2026 | D Hollins |
| Priya Shah | Hollins & Reed Contracting Ltd | 12 Jan 2026 | P Shah |
| Reece Ollerton | Hollins & Reed Contracting Ltd | 12 Jan 2026 | R Ollerton |
| Lee Bramhall | Brinnington Soft Strip Ltd | 12 Jan 2026 | L Bramhall |
| Callum Whittle | Davenport Rise Electrical Ltd | 12 Jan 2026 | C Whittle |
| Owen Tattersall (visitor) | Thornley Vale Estates Ltd | 14 Jan 2026 | O Tattersall |
| Kieran Tunnicliffe | Tanyard Air Ltd | 19 Jan 2026 | K Tunnicliffe |
| Mark Etchells | Offerton Interiors Ltd | 2 Feb 2026 | M Etchells |

# Welfare facilities

Toilets, washing, drinking water, changing and rest.

Hired cabins in the rear yard, on mains water and drainage, in place before 12 January: site office, two flushing toilets, basins with hot water, soap, towels, drinking water, lockers and drying, and a heated rest room with tables, chairs with backs, kettle and microwave.

# Fire and emergency procedures

What happens in a fire or other emergency.

The wired-in alarm stays on as long as possible; temporary linked call points and sounders go in before it comes out. Fire point at each exit. On the alarm, leave to the yard gate. Priya Shah checks the signing-in sheet. Exits stay clear. First aiders: Dan, Priya. Ring 999, then Dan.

# Work involving particular risks

| Work | Where it arises | The measures |
| --- | --- | --- |
| Burial, engulfment or falling from a height, particularly aggravated by the work or the site | Not on this job | Single storey: no floor edge, floor void, riser or shaft. Tower and step work only. Nobody goes on the roof. |
| Chemical or biological substances of particular danger, or needing health monitoring | Yes: drilling concrete and cutting blockwork | Extraction, masks, COSHH assessments, health checks where needed. Asbestos survey: none found. If unsure, stop. |
| Ionising radiation with controlled or supervised areas | Not on this job | No radiography or similar work. |
| Near high voltage power lines | Not on this job | No overhead lines over the unit or the yard. |
| Risk of drowning | Not on this job | All work is indoors, with no water nearby. |
| Wells, underground earthworks and tunnels | Not on this job | Nothing is dug. |
| Divers on a system of air supply | Not on this job | No work in water. |
| Caissons with a compressed air atmosphere | Not on this job | No caissons. |
| Explosives | Not on this job | No explosives or cartridge tools. |
| Assembly or dismantling of heavy prefabricated components | Not on this job | No crane. Everything comes through the rear doors in pieces. |

# Review and revision

When the plan is reviewed, and any significant change.

Dan Hollins reviews the plan after each Monday meeting, and whenever the work, the trades or the access change. A new revision goes to every contractor and to the principal designer, and the table on the cover says what changed.