## Site Diary
Site Diary
Hollins & Reed Contracting Ltd
Date |  |  | Project |  |  | Job number |  | Weather am |  | Weather pm
7 Sep 2026 |  |  | House extension, House 2 |  |  | HR-2407 |  | Rain, 16°C |  | Dry, 18°C
Trades on site |  |  |  |  | Company |  |  |  | No. |  | Hours
Site manager |  |  |  |  | Hollins & Reed Contracting Ltd |  |  |  | 1 |  | 9
Groundworkers |  |  |  |  | Hollins & Reed Groundworks Ltd |  |  |  | 4 |  | 8
Banksman |  |  |  |  | Hollins & Reed Contracting Ltd |  |  |  | 1 |  | 8
Pump operator |  |  |  |  | Hollins & Reed Concrete Pumping Ltd |  |  |  | 1 |  | 3.5
Plant and equipment |  |  |  |  | Supplier |  |  |  | No. |  | Hours
Concrete pump, boom |  |  |  |  | Hollins & Reed Concrete Pumping Ltd |  |  |  | 1 |  | 3.5
Vibrating tamper beam, petrol |  |  |  |  | Hollins & Reed Groundworks Ltd |  |  |  | 1 |  | 1
Area |  |  | Work carried out
Rear extension |  |  | Fixed 50 mm duct in the slab edge for the garden tap, as instructed: 2 groundworkers, 09:00 to 09:30, 1 hour in all.
Rear extension |  |  | Brushed rain water off the membrane, 10:00 to 10:20. Checked mesh, spacers and levels before the pour.
Rear extension |  |  | Poured the ground floor slab, 10:40 to 11:40. Slab 6.0 m by 4.7 m, 28 m², 150 mm thick: 4.2 m³.
Rear extension |  |  | Thickened edge on the 3 new sides, 15.4 m long, 300 mm wide, 175 mm below the slab: 0.8 m³. With the slab, the 5 m³ on the ticket.
Rear extension |  |  | Tamped and floated to 14:30. Covered with polythene at 15:30, as rain and wind are forecast tomorrow.
Front drive |  |  | Pump washed out into the lined pit by 12:10 and off site at 12:30. Drive swept.
Time |  | Deliveries |  |  |  |  | Supplier |  |  | Ticket no.
08:10 |  | Polythene sheet, 2 rolls, and spare spacers |  |  |  |  | Hollins & Reed Builders Merchants Ltd |  |  | M 20418
10:32 |  | RC25/30 concrete, 5 m³ |  |  |  |  | Hollins & Reed Concrete Ltd |  |  | C 48213
Time | Visitors |  |  |  |  | Company |  | Reason for visit
08:40 | Building control surveyor |  |  |  |  | Council building control |  | Looked at membrane and mesh before the pour. Nothing to change. Happy for us to pour.
14:50 | Client’s surveyor |  |  |  |  | Thornley Vale Estates Ltd |  | Saw the slab and the new duct.
From |  |  |  | Instructions received
Client, by phone 08:55 |  |  |  | Add a duct in the slab edge for a garden tap. I confirmed it by email at 09:10. It sits above the membrane, so the membrane is not cut. Rang the surveyor at 09:15 to say so; no need to come back. Cost to follow.
Delays and problems
Rain from 07:40 to 09:50, heavy at times. Pour held 1 hour. Rang the batching plant at 08:30 and moved the wagon from 09:30 to 10:30, before it was loaded. The pump was already on the road: on site 09:00, set up by 09:30.
Cost of the hold, 09:30 to 10:30: 1 hour each for the 4 groundworkers and the banksman, 5 hours in all, and the pump stood for the hour. Separate from the duct. No concrete wasted.
Worked example of a made-up job. Not a record of real work. · Page 1 of 2
Site Diary
Hollins & Reed Contracting Ltd
Date |  |  | Project |  |  | Job number |  | Weather am |  | Weather pm
7 Sep 2026 |  |  | House extension, House 2 |  |  | HR-2407 |  | Rain, 16°C |  | Dry, 18°C
Accidents, incidents and near misses
10:35, near miss. A neighbour walked behind the wagon on the shared drive as it reversed. Reece Ollerton, banksman, stopped the driver. Nobody hurt. Barrier put across the end of the drive and neighbours told the times. Reported to me at 10:40.
Signed |  |  |  |  | Name |  |  |  | Date
signed |  |  |  |  | Dan Hollins |  |  |  | 7 September 2026
Worked example of a made-up job. Not a record of real work. · Page 2 of 2