Site Diary Hollins & Reed Contracting Ltd

| Date 15 Sep 2026 |  | Project Office fit-out, Unit 3 |  | Job number HR-2402 |  | Weather am Dry, 16°C |  | Weather pm Dry, 18°C |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Trades on site | Company | No. | Hours |
| --- | --- | --- | --- |
| Site manager | Hollins & Reed Contracting Ltd | 1 | 9 |
| Electricians | Hollins & Reed Electrical Ltd | 3 | 8 |
| Plumbers | Hollins & Reed Plumbing Ltd | 2 | 8 |
| Heating engineers | Hollins & Reed Heating Ltd | 2 | 8 |
| Ceiling fixers | Hollins & Reed Interiors Ltd | 3 | 8 |
| Decorators | Hollins & Reed Decorating Ltd | 2 | 8 |
| Total on site | People and hours | 13 | 105 |

| Area | Work carried out |
| --- | --- |
| Open office | Ceiling fixers: finished the last of the grid by 08:30. Carried the tiles up 11:30 to 12:00. Laid them 12:30 to 16:30, 96 m² of the 140 m². 44 m² left for tomorrow. |
| Open office | Electricians: second fix of floor boxes, 18 of 24 done. |
| Open office | Heating engineers: hung 6 of 8 radiators. Pressure test tomorrow, once the last 2 are on. |
| Meeting room | Electricians: moved 2 double sockets as instructed, 13:00 to 14:30, 2 men, 3 hours in all. |
| Meeting room | Decorators: mist coat on the south and west walls. East and north walls left until tomorrow, for the 2 sockets moved between them. |
| Kitchen | Plumbers: fixed sink, taps and water heater. Tested at 15:00, no leaks. |
| Corridor | Decorators: first coat on the walls. |

Hold-ups

Ceiling tiles due by 08:00, arrived 11:30, ticket M 20577 from Hollins & Reed Builders Merchants Ltd. I rang them at 08:20 and they gave 11:30, so I told the client’s agent at 08:40.

Cost of the wait, 08:30 to 11:30: 3 hours each for the 3 ceiling fixers, 9 hours in all. No other work for them on this floor until the tiles came. The ceiling was due to finish today and now finishes tomorrow morning. Handover on 9 October still holds.

Instruction: at 10:15 the client’s agent asked for 2 double sockets in the meeting room to move from the east wall to the north wall. I confirmed it by email at 10:40. Cost to follow: 3 hours for the electricians, making good the old and new socket positions, and 2 walls painted a day later.

| Signed signed |  | Name Dan Hollins |  | Date 15 September 2026 |
| --- | --- | --- | --- | --- |