## Site Diary
Site Diary
Hollins & Reed Contracting Ltd
Date | Project | Job number | Weather am | Weather pm
15 Sep 2026 | Office fit-out, Unit 3 | HR-2402 | Dry, 16°C | Dry, 18°C
Trades on site |  | Company | No. | Hours
Site manager |  | Hollins & Reed Contracting Ltd | 1 | 9
Electricians |  | Hollins & Reed Electrical Ltd | 3 | 8
Plumbers |  | Hollins & Reed Plumbing Ltd | 2 | 8
Heating engineers |  | Hollins & Reed Heating Ltd | 2 | 8
Ceiling fixers |  | Hollins & Reed Interiors Ltd | 3 | 8
Decorators |  | Hollins & Reed Decorating Ltd | 2 | 8
Total on site |  | People and hours | 13 | 105
Area | Work carried out
Open office | Ceiling fixers: finished the last of the grid by 08:30. Carried the tiles up 11:30 to 12:00. Laid them 12:30 to 16:30, 96 m² of the 140 m². 44 m² left for tomorrow.
Open office | Electricians: second fix of floor boxes, 18 of 24 done.
Open office | Heating engineers: hung 6 of 8 radiators. Pressure test tomorrow, once the last 2 are on.
Meeting room | Electricians: moved 2 double sockets as instructed, 13:00 to 14:30, 2 men, 3 hours in all.
Meeting room | Decorators: mist coat on the south and west walls. East and north walls left until tomorrow, for the 2 sockets moved between them.
Kitchen | Plumbers: fixed sink, taps and water heater. Tested at 15:00, no leaks.
Corridor | Decorators: first coat on the walls.
Hold-ups
Ceiling tiles due by 08:00, arrived 11:30, ticket M 20577 from Hollins & Reed Builders Merchants Ltd. I rang them at 08:20 and they gave 11:30, so I told the client’s agent at 08:40.
Cost of the wait, 08:30 to 11:30: 3 hours each for the 3 ceiling fixers, 9 hours in all. No other work for them on this floor until the tiles came. The ceiling was due to finish today and now finishes tomorrow morning. Handover on 9 October still holds.
Instruction: at 10:15 the client’s agent asked for 2 double sockets in the meeting room to move from the east wall to the north wall. I confirmed it by email at 10:40. Cost to follow: 3 hours for the electricians, making good the old and new socket positions, and 2 walls painted a day later.
Signed |  | Name | Date
signed |  | Dan Hollins | 15 September 2026
Worked example of a made-up job. Not a record of real work.