## Weekly Site Diary
Weekly Site Diary
Hollins & Reed Contracting Ltd
Week commencing |  | Project |  | Job number
Monday 14 September 2026 |  | Re-roof, House 6 |  | HR-2415
Day | Work carried out | Labour on site | Weather | Delays and instructions
Monday | Scaffold inspected 07:15 to 08:00, before anyone went up, tag signed. Stripped rear slope, checked rafters, underlay and battens on before leaving. Tiles delivered 11:00, stacked by the scaffold. | Hollins & Reed Roofing Ltd: roofers 4, labourer 1, 8 hours. Hollins & Reed Scaffolding Ltd: inspector 1, 0.75 hours. | Dry, cloudy, 19°C. Wind 12 mph mean | None
Tuesday | Stripped front slope, underlay and battens on before leaving. Both slopes now covered. Old tiles down the chute to the skip. | Hollins & Reed Roofing Ltd: roofers 4, labourer 1, 8 hours | Dry, breezy, 18°C. Wind 15 mph mean | None
Wednesday | No roof work. Checked underlay and battens from the scaffold at 08:00, all secure. Came down when the wind rose. Scaffold out of use until inspected. Stood down at 09:30. | Hollins & Reed Roofing Ltd: roofers 4, labourer 1, 1.5 hours | Showers, 16°C. Wind at the eaves 25 mph mean, gusts 38 mph at 09:00 | Lost day 1. Over our stop limit of 23 mph mean, gusting 35 mph. Client told by email at 09:40.
Thursday | No roof work. Nobody on the scaffold, still out of use. Looked over the roof from the ground at 08:00, nothing lifted. Stood down at 08:30. | Hollins & Reed Roofing Ltd: roofers 4, labourer 1, 0.5 hours | Rain am, 15°C. Wind read from the ground 27 mph mean, gusts 41 mph at 08:00 | Lost day 2. Same limit. Client told by email at 08:45. Finish now 2 working days later.
Friday | Scaffold inspected 07:15 to 08:00 after the wind, before anyone went up, tag signed. Underlay and battens checked, none lifted, no water in. Tiles loaded out evenly. Tiled the rear slope. Front slope stays covered. | Hollins & Reed Roofing Ltd: roofers 4, labourer 1, 8 hours. Hollins & Reed Scaffolding Ltd: inspector 1, 0.75 hours. | Dry, bright, 17°C. Wind 13 mph mean | None
Signed |  |  | Date
signed |  |  | 18 September 2026
Worked example of a made-up job. Not a record of real work.