## Confined Space Entry Permit
Confined Space Entry Permit
Hollins & Reed Contracting Ltd
Permit no. |  | Site | [11 empty] | Exact location
HR-0420 |  | Unit 3, Canal Side Business Park | [11 empty] | Foul manhole MH2, east yard
Details
Contractor | Hollins & Reed |  |  |  |  | Issued to |  |  |  |  | Priya Shah | [5 empty] | Valid from | [7 empty] | 15/10/26 09:00
Valid to | 15/10/26 14:00 |  |  |  |  | RAMS ref |  |  |  |  | HR-RAMS-10 | [5 empty] | Isolation cert | [7 empty] | Stopper T1
The work
Space and entry point |  |  | Foul manhole MH2, 2.4 m deep, 1.2 m across. One entry, the top cover.
Work to be done |  |  | Join the new drain through the chamber wall. Two to lift the pipe. Make good the benching.
Why entry, time limit |  |  | The joint cannot be made from the surface. Two entries, 45 minutes each.
Hazards
Oxygen low or high |  | ☒ | Toxic gas | [6 empty] | ☒ |  | Flammable air | [7 empty] | ☒ | Engulfment | [6 empty] | ☒
Heat |  | ☐ | Drowning | [6 empty] | ☒ |  | Restricted entry | [7 empty] | ☒ | Power, machinery | [6 empty] | ☐
Precautions | [15 empty] | Done | [5 empty] | By
Space isolated and locked off | [15 empty] | ☒ | [5 empty] | Priya Shah, tied off
Cleaned, purged and ventilated | [15 empty] | ☒ | [5 empty] | Reece Ollerton, fan on
Air tested before entry and during | [15 empty] | ☒ | [5 empty] | Priya Shah
Supervisor and top person named | [15 empty] | ☒ | [5 empty] | Dan Hollins, Priya Shah
Communication agreed | [15 empty] | ☒ | [5 empty] | Radio and line signals
Rescue plan and equipment ready | [15 empty] | ☒ | [5 empty] | Dan Hollins, drilled
Harness and line | [15 empty] | ☒ | [5 empty] | Both entrants
Safe lighting and tools | [15 empty] | ☒ | [5 empty] | Rated for the space
Breathing apparatus where needed | [15 empty] | ☐ | [5 empty] | Not needed. Escape sets
How emergency services are called | [15 empty] | ☒ | [5 empty] | Priya Shah, 999
What is isolated | [6 empty] | How | [7 empty] | Locked |  |  |  | Tag |  |  |  |  | Proved by
Incoming foul drain | [6 empty] | Stopper at MH1, tied off | [7 empty] | ☐ |  |  |  | T1 |  |  |  |  | Priya Shah
Equipment
Gas monitor |  | ☒ | Tripod and winch | [6 empty] | ☒ |  | Escape BA | [7 empty] | ☒ | Radio | [6 empty] | ☒
Lighting |  | ☒ | [7 empty] | ☐ | [9 empty] | ☐ | [7 empty] | ☐
Other conditions
Out on any alarm, falling oxygen or a reading moving towards a limit. Our limits CO 20 ppm, H2S 5 ppm, gas 10% LEL.
Test oxygen, then gas, then toxics, from the top by probe. Top person stays out. Rescue by winch from the surface.
Sign-off |  |  |  |  | Name | [8 empty] | Signature | [9 empty] | Date |  |  | Time
Issued: precautions checked |  |  |  |  | Dan Hollins | [8 empty] | signed | [9 empty] | 15/10/26 |  |  | 08:55
Accepted: permit understood |  |  |  |  | Priya Shah | [8 empty] | signed | [9 empty] | 15/10/26 |  |  | 09:00
Worked example of a made-up job. Not a permit. · Page 1 of 2
Confined Space Entry Permit
Hollins & Reed Contracting Ltd
Permit no. |  | Site | [11 empty] | Exact location
HR-0420 |  | Unit 3, Canal Side Business Park | [11 empty] | Foul manhole MH2, east yard
Gas tests
Time | O2 % |  |  | LEL % |  |  |  |  | CO ppm |  |  |  | H2S ppm |  |  |  |  | By
08:40 | 20.8 |  |  | 0 |  |  |  |  | 0 |  |  |  | 1 |  |  |  |  | Priya Shah
09:10 | 20.9 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  |  | Priya Shah
09:50 | 20.9 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  |  | Priya Shah
11:00 | 20.8 |  |  | 0 |  |  |  |  | 0 |  |  |  | 1 |  |  |  |  | Priya Shah
11:40 | 20.9 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  |  | Priya Shah
People in the space: name | [7 empty] | Company | [9 empty] | Briefed |  |  |  |  | In |  |  | Out
Reece Ollerton | [7 empty] | Hollins & Reed | [9 empty] | ☒ |  |  |  |  | 09:15 |  |  | 09:55
Joe Penketh | [7 empty] | Hollins & Reed | [9 empty] | ☒ |  |  |  |  | 09:15 |  |  | 09:55
Reece Ollerton | [7 empty] | Hollins & Reed | [9 empty] | ☒ |  |  |  |  | 11:05 |  |  | 11:45
Joe Penketh | [7 empty] | Hollins & Reed | [9 empty] | ☒ |  |  |  |  | 11:05 |  |  | 11:45
☐
☐
Cancellation
All out at |  |  | 11:45. Both entrants counted out.
Space secured |  |  | Cover back on at 12:10. Stopper out at MH1, drain running.
Equipment removed |  |  | Tripod, fan, monitors and lines off the yard by 12:30.
Handback
Isolations removed |  |  | Stopper T1 removed by Priya Shah at 12:05
Area returned to |  |  | Thornley Vale Estates Ltd, site keyholder
Notes |  |  | Readings in the job file. Both entrants washed down after each entry.
Sign-off |  |  |  |  | Name | [8 empty] | Signature | [9 empty] | Date |  |  | Time
Extended: new end time |  |  |  |  | Not extended
Cancelled: area checked |  |  |  |  | Dan Hollins | [8 empty] | signed | [9 empty] | 15/10/26 |  |  | 12:35
Handed back: area returned |  |  |  |  | Dan Hollins | [8 empty] | signed | [9 empty] | 15/10/26 |  |  | 12:40
Worked example of a made-up job. Not a permit. · Page 2 of 2