## Permit to Dig
Permit to Dig
Hollins & Reed Contracting Ltd
Permit no. |  | Site | [10 empty] | Exact location
HR-0419 |  | Unit 3, Canal Side Business Park | [10 empty] | East yard, gully to manhole MH2
Details
Contractor | Hollins & Reed |  |  |  |  | Issued to |  |  |  | Priya Shah | [5 empty] | Valid from | [5 empty] | 14/10/26 08:00
Valid to | 14/10/26 16:30 |  |  |  |  | RAMS ref |  |  |  | HR-RAMS-09 | [5 empty] | Drawing, date | [5 empty] | HR-D-02, 05/10/26
The work
Where, depth, method |  |  | Trench 6 m long, 1.2 m deep. Breaker through concrete, then mini excavator with a spotter.
Hand dig zone |  |  | Hand tools only near marked lines. Breaker 500 mm off them. Insulated tools by the cable.
Hazards
Electricity |  | ☒ | Gas |  |  |  |  | ☒ |  |  | Water | [6 empty] | ☒ | Telecoms | [5 empty] | ☐
Drains and sewers |  | ☒ | District heating |  |  |  |  | ☐ |  |  | Contaminated ground | [6 empty] | ☐ | Unstable ground | [5 empty] | ☒
Water ingress |  | ☒ | Traffic |  |  |  |  | ☒ |  |  | Services unknown | [6 empty] | ☐ | [6 empty] | ☐
Precautions | [14 empty] | Done |  |  |  |  | By
Drawings obtained and dated | [14 empty] | ☒ |  |  |  |  | Dan Hollins, 05/10/26
Scanned with locator and signal generator | [14 empty] | ☒ |  |  |  |  | Dan Hollins, 13/10/26
Services marked on the plan and ground | [14 empty] | ☒ |  |  |  |  | Dan Hollins
Trial holes hand dug | [14 empty] | ☒ |  |  |  |  | Priya Shah, two holes
Services exposed and supported | [14 empty] | ☐ |  |  |  |  | Not needed. None crossed
Edge protection and ladders in place | [14 empty] | ☒ |  |  |  |  | Reece Ollerton
Spoil kept back from the edge | [14 empty] | ☒ |  |  |  |  | Reece Ollerton
Sides supported or battered | [14 empty] | ☒ |  |  |  |  | Priya Shah, supports
Inspected at the start of each shift | [14 empty] | ☒ |  |  |  |  | Dan Hollins
Gas monitoring, traffic management | [14 empty] | ☒ |  |  |  |  | Reece Ollerton, barriers
Services made dead | [6 empty] | How | [6 empty] | Locked |  |  | Tag |  |  |  | Proved by
Nothing isolated | [6 empty] | All services stay live | [6 empty] | ☐
People on this permit: name | [8 empty] | Company | [13 empty] | Briefed
Priya Shah | [8 empty] | Hollins & Reed | [13 empty] | ☒
Reece Ollerton | [8 empty] | Hollins & Reed | [13 empty] | ☒
Other conditions
Treat every service as live. Re-scan as the trench deepens. Unknown service, stop and ring 0161 496 0142.
Cable struck, driver stays in the cab. Nobody goes near until the owner makes it safe.
Sign-off |  |  |  |  | Name | [7 empty] | Signature | [7 empty] | Date |  |  | Time
Issued: precautions checked |  |  |  |  | Dan Hollins | [7 empty] | signed | [7 empty] | 14/10/26 |  |  | 07:45
Accepted: permit understood |  |  |  |  | Priya Shah | [7 empty] | signed | [7 empty] | 14/10/26 |  |  | 07:50
Worked example of a made-up job. Not a permit. · Page 1 of 2
Permit to Dig
Hollins & Reed Contracting Ltd
Permit no. |  | Site | [10 empty] | Exact location
HR-0419 |  | Unit 3, Canal Side Business Park | [10 empty] | East yard, gully to manhole MH2
Excavation inspections
Date | Time |  |  | By | [7 empty] | Result
14/10/26 | 13:00 |  |  | Dan Hollins | [7 empty] | Trench at 0.9 m. Supports in, sides sound, barriers up.
15/10/26 | 07:45 |  |  | Dan Hollins | [7 empty] | Start of shift, after rain. Pumped out. Sides sound.
15/10/26 | 12:45 |  |  | Dan Hollins | [7 empty] | Before backfilling. Sides, supports and barriers sound.
Cancellation
Backfilled or secured |  |  | Backfilled in layers. Concrete reinstated 15 October. No concrete around services.
Services as found |  |  | Cable and gas pipe where the drawing shows. Neither touched.
Drawings marked up |  |  | New drain added to HR-D-02. Copy to the site plan.
Handback
Isolations removed |  |  | None were made
Area returned to |  |  | Thornley Vale Estates Ltd, site keyholder
Notes |  |  | Yard open again. Barriers gone.
Sign-off |  |  |  |  | Name | [7 empty] | Signature | [7 empty] | Date |  |  | Time
Extended: new end time |  |  |  |  | Dan Hollins, to 15/10 16:00 | [7 empty] | signed | [7 empty] | 14/10/26 |  |  | 16:15
Cancelled: area checked |  |  |  |  | Dan Hollins | [7 empty] | signed | [7 empty] | 15/10/26 |  |  | 15:30
Handed back: area returned |  |  |  |  | Dan Hollins | [7 empty] | signed | [7 empty] | 15/10/26 |  |  | 15:40
Worked example of a made-up job. Not a permit. · Page 2 of 2