Snagging List Hollins & Reed Contracting Ltd

| Project New homes, Phase 2 | Plot or area Plots 4 to 9 | Inspected by Dan Hollins | Date 6 October 2026 |
| --- | --- | --- | --- |

| No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Plot 4 drive | Over 10 mm out under a 2 m straight edge | Medium | Surfacing | 06/10/26 | 13/10/26 | ☒ | DH 08/10/26 |
| 2 | Plot 4 drive | Standing water an hour after rain, over 5 mm deep | High | Surfacing | 06/10/26 | 08/10/26 | ☒ | DH 08/10/26 |
| 3 | Plot 5 path | Standing water at the entrance door | High | Groundworker | 06/10/26 | 08/10/26 | ☒ | DH 08/10/26 |
| 4 | Plot 5 drive | Falls towards the building | High | Groundworker | 06/10/26 | 08/10/26 | ☐ |  |
| 5 | Plot 6 drive | Block rocking by the garage door | Medium | Paving | 06/10/26 | 13/10/26 | ☒ | DH 08/10/26 |
| 6 | Plot 6 drive | Blocks cracked and chipped | Medium | Paving | 06/10/26 | 13/10/26 | ☒ | DH 08/10/26 |
| 7 | Plot 6 drive | Block joints not filled to the surface | Low | Paving | 06/10/26 | 16/10/26 | ☒ | DH 08/10/26 |
| 8 | Plot 7 drive | Pattern not consistent across the drive | Low | Paving | 06/10/26 | 16/10/26 | ☐ |  |
| 9 | Plot 7 drive | Rough cuts around the manhole | Low | Paving | 06/10/26 | 16/10/26 | ☐ |  |
| 10 | Plot 7 drive | Edge blocks not haunched and not firm | Medium | Paving | 06/10/26 | 13/10/26 | ☐ |  |
| 11 | Plot 8 frontage | Kerb loose | Medium | Groundworker | 06/10/26 | 13/10/26 | ☒ | DH 08/10/26 |
| 12 | Plot 8 drive | Roller marks in the tarmac | Low | Surfacing | 06/10/26 | 16/10/26 | ☐ |  |
| 13 | Plot 8 drive | Loose aggregate on the surface | Low | Surfacing | 06/10/26 | 16/10/26 | ☐ |  |
| 14 | Plot 8 drive | Ridge at the joint between two laying sessions | Medium | Surfacing | 06/10/26 | 13/10/26 | ☐ |  |
| 15 | Plot 9 drive | Tarmac cracking at the threshold | Medium | Surfacing | 06/10/26 | 13/10/26 | ☐ |  |
| 16 | Plot 9 drive | Tyre marks and indentations from plant | Medium | Surfacing | 06/10/26 | 13/10/26 | ☐ |  |

Snagging List Hollins & Reed Contracting Ltd

| Project New homes, Phase 2 | Plot or area Plots 4 to 9 | Inspected by Dan Hollins | Date 6 October 2026 |
| --- | --- | --- | --- |

| No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 17 | Plot 9 frontage | Trench reinstatement does not match the surface | Medium | Surfacing | 06/10/26 | 13/10/26 | ☐ |  |
| 18 | Shared drive | Oil stain on the blocks | Low | Paving | 06/10/26 | 16/10/26 | ☒ | DH 08/10/26 |
| 19 | Plot 5 drive | Mortar splashes on the paving | Low | Paving | 06/10/26 | 16/10/26 | ☒ | DH 08/10/26 |
| 20 | Plot 4 frontage | Temporary signage and cable ties left | Low | Site team | 06/10/26 | 16/10/26 | ☒ | DH 08/10/26 |
| 21 | Shared path | Slab raised, trip hazard | High | Paving | 06/10/26 | 08/10/26 | ☒ | DH 08/10/26 |
| 22 | Shared drive entrance | Dropped kerb step over 6 mm | High | Groundworker | 06/10/26 | 08/10/26 | ☐ |  |
| 23 | Plot 7 drive | Drain cover not in line with the ground, rocks | High | Drainage | 06/10/26 | 08/10/26 | ☒ | DH 08/10/26 |
| 24 | Plot 4 frontage | Gully full of debris | Medium | Drainage | 06/10/26 | 13/10/26 | ☒ | DH 08/10/26 |
| 25 | Plot 6 frontage | Gully slow to drain | Medium | Drainage | 06/10/26 | 13/10/26 | ☐ |  |
| 26 | Shared drive | Surface water does not reach the gully, bucket test | Medium | Groundworker | 06/10/26 | 13/10/26 | ☐ |  |
| 27 | Visitor bays | Permeable paving does not soak through | Medium | Paving | 06/10/26 | 13/10/26 | ☐ |  |
| 28 | SuDS feature | Inlet blocked by overgrown planting | Medium | Landscaper | 06/10/26 | 13/10/26 | ☐ |  |
| 29 | Plots 4 and 5 boundary | Fence panel leaning | Medium | Fencing | 06/10/26 | 13/10/26 | ☒ | DH 08/10/26 |
| 30 | Plots 5 and 6 boundary | Fence post loose | Medium | Fencing | 06/10/26 | 13/10/26 | ☒ | DH 08/10/26 |
| 31 | Plot 6 boundary | Gravel board missing | Low | Fencing | 06/10/26 | 16/10/26 | ☐ |  |

Snagging List Hollins & Reed Contracting Ltd

| Project New homes, Phase 2 | Plot or area Plots 4 to 9 | Inspected by Dan Hollins | Date 6 October 2026 |
| --- | --- | --- | --- |

| No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 32 | Plot 7 boundary | Gap under the fence | Low | Fencing | 06/10/26 | 16/10/26 | ☐ |  |
| 33 | Plot 8 boundary | Fence not in the position shown on the plan | High | Fencing | 06/10/26 | 08/10/26 | ☐ |  |
| 34 | Plot 9 side gate | Gate will not latch shut | Medium | Fencing | 06/10/26 | 13/10/26 | ☐ |  |
| 35 | Plot 9 side gate | Timber not protected | Low | Fencing | 06/10/26 | 16/10/26 | ☐ |  |
| 36 | Plot 8 rear | Retaining wall cracked | High | Groundworker | 06/10/26 | 08/10/26 | ☐ |  |
| 37 | Plot 4 rear garden | Turf not evenly laid, gaps showing | Medium | Landscaper | 06/10/26 | 13/10/26 | ☐ |  |
| 38 | Plot 5 rear garden | Bare soil where turf should be | Medium | Landscaper | 06/10/26 | 13/10/26 | ☐ |  |
| 39 | Plot 6 rear garden | Dip in the turf | Low | Landscaper | 06/10/26 | 16/10/26 | ☐ |  |
| 40 | Plot 7 front garden | Two shrubs dead | Medium | Landscaper | 06/10/26 | 13/10/26 | ☐ |  |
| 41 | Site entrance | Planting differs from the approved plan | Medium | Landscaper | 06/10/26 | 13/10/26 | ☐ |  |
| 42 | Site entrance | Tree root flare buried by mulch | Medium | Landscaper | 06/10/26 | 13/10/26 | ☐ |  |
| 43 | Plot 5 rear | Outdoor light not working | Medium | Electrician | 06/10/26 | 13/10/26 | ☐ |  |
| 44 | Plot 6 rear | Patio slabs rock underfoot | Medium | Paving | 06/10/26 | 13/10/26 | ☐ |  |
| 45 | Bin store | Step at the entrance, bins cannot be wheeled out | Medium | Groundworker | 06/10/26 | 13/10/26 | ☐ |  |
| 46 | Plot 8 side | Meter box door will not shut | Low | Site team | 06/10/26 | 16/10/26 | ☐ |  |
| 47 | Visitor bays | Bay markings missing | Low | Surfacing | 06/10/26 | 16/10/26 | ☐ |  |

Snagging List Hollins & Reed Contracting Ltd

| Project New homes, Phase 2 | Plot or area Plots 4 to 9 | Inspected by Dan Hollins | Date 6 October 2026 |
| --- | --- | --- | --- |

| No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 48 | Plot 7 rear garden | Builder’s materials left | Low | Site team | 06/10/26 | 16/10/26 | ☐ |  |
| 49 |  |  |  |  |  |  | ☐ |  |
| 50 |  |  |  |  |  |  | ☐ |  |
| 51 |  |  |  |  |  |  | ☐ |  |
| 52 |  |  |  |  |  |  | ☐ |  |
| 53 |  |  |  |  |  |  | ☐ |  |
| 54 |  |  |  |  |  |  | ☐ |  |
| 55 |  |  |  |  |  |  | ☐ |  |
| 56 |  |  |  |  |  |  | ☐ |  |
| 57 |  |  |  |  |  |  | ☐ |  |
| 58 |  |  |  |  |  |  | ☐ |  |
| 59 |  |  |  |  |  |  | ☐ |  |
| 60 |  |  |  |  |  |  | ☐ |  |
| 61 |  |  |  |  |  |  | ☐ |  |
| 62 |  |  |  |  |  |  | ☐ |  |
| 63 |  |  |  |  |  |  | ☐ |  |