## Snagging List
Snagging List
Hollins & Reed Contracting Ltd
Project |  |  | Plot or area | Inspected by |  | Date
New homes, Phase 2 |  |  | Plots 4 to 9 | Dan Hollins |  | 6 October 2026
No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off
1 | Plot 4 drive | Over 10 mm out under a 2 m straight edge | Medium | Surfacing | 06/10/26 | 13/10/26 | ☒ | DH 08/10/26
2 | Plot 4 drive | Standing water an hour after rain, over 5 mm deep | High | Surfacing | 06/10/26 | 08/10/26 | ☒ | DH 08/10/26
3 | Plot 5 path | Standing water at the entrance door | High | Groundworker | 06/10/26 | 08/10/26 | ☒ | DH 08/10/26
4 | Plot 5 drive | Falls towards the building | High | Groundworker | 06/10/26 | 08/10/26 | ☐
5 | Plot 6 drive | Block rocking by the garage door | Medium | Paving | 06/10/26 | 13/10/26 | ☒ | DH 08/10/26
6 | Plot 6 drive | Blocks cracked and chipped | Medium | Paving | 06/10/26 | 13/10/26 | ☒ | DH 08/10/26
7 | Plot 6 drive | Block joints not filled to the surface | Low | Paving | 06/10/26 | 16/10/26 | ☒ | DH 08/10/26
8 | Plot 7 drive | Pattern not consistent across the drive | Low | Paving | 06/10/26 | 16/10/26 | ☐
9 | Plot 7 drive | Rough cuts around the manhole | Low | Paving | 06/10/26 | 16/10/26 | ☐
10 | Plot 7 drive | Edge blocks not haunched and not firm | Medium | Paving | 06/10/26 | 13/10/26 | ☐
11 | Plot 8 frontage | Kerb loose | Medium | Groundworker | 06/10/26 | 13/10/26 | ☒ | DH 08/10/26
12 | Plot 8 drive | Roller marks in the tarmac | Low | Surfacing | 06/10/26 | 16/10/26 | ☐
13 | Plot 8 drive | Loose aggregate on the surface | Low | Surfacing | 06/10/26 | 16/10/26 | ☐
14 | Plot 8 drive | Ridge at the joint between two laying sessions | Medium | Surfacing | 06/10/26 | 13/10/26 | ☐
15 | Plot 9 drive | Tarmac cracking at the threshold | Medium | Surfacing | 06/10/26 | 13/10/26 | ☐
16 | Plot 9 drive | Tyre marks and indentations from plant | Medium | Surfacing | 06/10/26 | 13/10/26 | ☐
Worked example. Change it to fit your job before you use it.
Page 1 of 4
Snagging List
Hollins & Reed Contracting Ltd
Project |  |  | Plot or area | Inspected by |  | Date
New homes, Phase 2 |  |  | Plots 4 to 9 | Dan Hollins |  | 6 October 2026
No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off
17 | Plot 9 frontage | Trench reinstatement does not match the surface | Medium | Surfacing | 06/10/26 | 13/10/26 | ☐
18 | Shared drive | Oil stain on the blocks | Low | Paving | 06/10/26 | 16/10/26 | ☒ | DH 08/10/26
19 | Plot 5 drive | Mortar splashes on the paving | Low | Paving | 06/10/26 | 16/10/26 | ☒ | DH 08/10/26
20 | Plot 4 frontage | Temporary signage and cable ties left | Low | Site team | 06/10/26 | 16/10/26 | ☒ | DH 08/10/26
21 | Shared path | Slab raised, trip hazard | High | Paving | 06/10/26 | 08/10/26 | ☒ | DH 08/10/26
22 | Shared drive entrance | Dropped kerb step over 6 mm | High | Groundworker | 06/10/26 | 08/10/26 | ☐
23 | Plot 7 drive | Drain cover not in line with the ground, rocks | High | Drainage | 06/10/26 | 08/10/26 | ☒ | DH 08/10/26
24 | Plot 4 frontage | Gully full of debris | Medium | Drainage | 06/10/26 | 13/10/26 | ☒ | DH 08/10/26
25 | Plot 6 frontage | Gully slow to drain | Medium | Drainage | 06/10/26 | 13/10/26 | ☐
26 | Shared drive | Surface water does not reach the gully, bucket test | Medium | Groundworker | 06/10/26 | 13/10/26 | ☐
27 | Visitor bays | Permeable paving does not soak through | Medium | Paving | 06/10/26 | 13/10/26 | ☐
28 | SuDS feature | Inlet blocked by overgrown planting | Medium | Landscaper | 06/10/26 | 13/10/26 | ☐
29 | Plots 4 and 5 boundary | Fence panel leaning | Medium | Fencing | 06/10/26 | 13/10/26 | ☒ | DH 08/10/26
30 | Plots 5 and 6 boundary | Fence post loose | Medium | Fencing | 06/10/26 | 13/10/26 | ☒ | DH 08/10/26
31 | Plot 6 boundary | Gravel board missing | Low | Fencing | 06/10/26 | 16/10/26 | ☐
Worked example. Change it to fit your job before you use it.
Page 2 of 4
Snagging List
Hollins & Reed Contracting Ltd
Project |  |  | Plot or area | Inspected by |  | Date
New homes, Phase 2 |  |  | Plots 4 to 9 | Dan Hollins |  | 6 October 2026
No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off
32 | Plot 7 boundary | Gap under the fence | Low | Fencing | 06/10/26 | 16/10/26 | ☐
33 | Plot 8 boundary | Fence not in the position shown on the plan | High | Fencing | 06/10/26 | 08/10/26 | ☐
34 | Plot 9 side gate | Gate will not latch shut | Medium | Fencing | 06/10/26 | 13/10/26 | ☐
35 | Plot 9 side gate | Timber not protected | Low | Fencing | 06/10/26 | 16/10/26 | ☐
36 | Plot 8 rear | Retaining wall cracked | High | Groundworker | 06/10/26 | 08/10/26 | ☐
37 | Plot 4 rear garden | Turf not evenly laid, gaps showing | Medium | Landscaper | 06/10/26 | 13/10/26 | ☐
38 | Plot 5 rear garden | Bare soil where turf should be | Medium | Landscaper | 06/10/26 | 13/10/26 | ☐
39 | Plot 6 rear garden | Dip in the turf | Low | Landscaper | 06/10/26 | 16/10/26 | ☐
40 | Plot 7 front garden | Two shrubs dead | Medium | Landscaper | 06/10/26 | 13/10/26 | ☐
41 | Site entrance | Planting differs from the approved plan | Medium | Landscaper | 06/10/26 | 13/10/26 | ☐
42 | Site entrance | Tree root flare buried by mulch | Medium | Landscaper | 06/10/26 | 13/10/26 | ☐
43 | Plot 5 rear | Outdoor light not working | Medium | Electrician | 06/10/26 | 13/10/26 | ☐
44 | Plot 6 rear | Patio slabs rock underfoot | Medium | Paving | 06/10/26 | 13/10/26 | ☐
45 | Bin store | Step at the entrance, bins cannot be wheeled out | Medium | Groundworker | 06/10/26 | 13/10/26 | ☐
46 | Plot 8 side | Meter box door will not shut | Low | Site team | 06/10/26 | 16/10/26 | ☐
47 | Visitor bays | Bay markings missing | Low | Surfacing | 06/10/26 | 16/10/26 | ☐
Worked example. Change it to fit your job before you use it.
Page 3 of 4
Snagging List
Hollins & Reed Contracting Ltd
Project |  |  | Plot or area | Inspected by |  | Date
New homes, Phase 2 |  |  | Plots 4 to 9 | Dan Hollins |  | 6 October 2026
No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off
48 | Plot 7 rear garden | Builder’s materials left | Low | Site team | 06/10/26 | 16/10/26 | ☐
49 | [6 empty] | ☐
50 | [6 empty] | ☐
51 | [6 empty] | ☐
52 | [6 empty] | ☐
53 | [6 empty] | ☐
54 | [6 empty] | ☐
55 | [6 empty] | ☐
56 | [6 empty] | ☐
57 | [6 empty] | ☐
58 | [6 empty] | ☐
59 | [6 empty] | ☐
60 | [6 empty] | ☐
61 | [6 empty] | ☐
62 | [6 empty] | ☐
63 | [6 empty] | ☐
Worked example. Change it to fit your job before you use it.
Page 4 of 4