Snag Sheet Hollins & Reed Contracting Ltd

| Project House extension, House 9 | Trade or subcontractor Second-fix joiner | Issued by Dan Hollins | Complete by 2 October 2026 |
| --- | --- | --- | --- |

| No. | Location | Description of snag | Priority | Done | Date done | Initials |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Utility door | Catches at the head and needs force to close | Medium | ☒ | 30/09/26 | PS |
| 2 | WC door | Will not latch | Medium | ☒ | 30/09/26 | PS |
| 3 | Bedroom 4 door | Gap to the jamb over 4 mm | Medium | ☒ | 30/09/26 | PS |
| 4 | Bedroom 4 door | Lining more than 5 mm out of plumb | Medium | ☐ |  |  |
| 5 | En-suite door | Door distorted more than 5 mm over its height | Medium | ☐ |  |  |
| 6 | Kitchen-diner door | Gap under the door too small for the floor covering | Medium | ☐ |  |  |
| 7 | Landing cupboard door | Hinge not flush, screw missing | Medium | ☒ | 30/09/26 | PS |
| 8 | Bedroom 4 door | Door stop not fitted | Low | ☒ | 30/09/26 | PS |
| 9 | Utility door | Handle loose | Medium | ☒ | 30/09/26 | PS |
| 10 | En-suite door | Thumbturn does not engage | High | ☒ | 30/09/26 | PS |
| 11 | Hall door | Architrave reveal not the same on both sides | Low | ☐ |  |  |
| 12 | Bedroom 4 door | Architrave not parallel to the lining | Low | ☐ |  |  |
| 13 | Kitchen-diner door | Architrave mitre open at the head | Low | ☐ |  |  |
| 14 | Landing door | Architrave leg not cut square to the skirting | Low | ☐ |  |  |
| 15 | Kitchen-diner, window corner | Internal skirting corner mitred and opening up, scribe it | Low | ☐ |  |  |
| 16 | Hall, wall end | External skirting mitre open | Low | ☐ |  |  |
| 17 | Kitchen-diner, long wall | Skirting joints not consistent, seen at 2 m in daylight | Low | ☐ |  |  |
| 18 | Bedroom 4 | Skirting gap to the floor over 5 mm, no covering laid | Medium | ☐ |  |  |
| 19 | Utility | Skirting loose, gap to the wall | Medium | ☐ |  |  |
| 20 | Utility, by boiler pipes | Skirting not scribed around the pipe | Low | ☐ |  |  |
| 21 | Bedroom 4 | Skirting fixed only at the ends and gapping | Medium | ☐ |  |  |
| 22 | En-suite | Pipe boxing not square | Low | ☐ |  |  |
| 23 | Bedroom 4 window | Window board not level across its depth | Medium | ☐ |  |  |
| 24 | Kitchen-diner window | Seal missing at the window board | Low | ☐ |  |  |

Snag Sheet Hollins & Reed Contracting Ltd

| Project House extension, House 9 | Trade or subcontractor Second-fix joiner | Issued by Dan Hollins | Complete by 2 October 2026 |
| --- | --- | --- | --- |

| No. | Location | Description of snag | Priority | Done | Date done | Initials |
| --- | --- | --- | --- | --- | --- | --- |
| 25 | Bedroom 4 window | Window board not scribed to the reveal, gap showing | Low | ☐ |  |  |
| 26 | Stairs | Handrail loose | High | ☒ | 30/09/26 | PS |
| 27 | Stairs | Handrail fixed to plasterboard alone, fix to the stud | High | ☐ |  |  |
| 28 | Stairs | Tread 6 loose | High | ☒ | 30/09/26 | PS |
| 29 | Stairs | Gap between tread 2 and the string | Low | ☐ |  |  |
| 30 | Stairs | Two balusters loose | High | ☒ | 30/09/26 | PS |
| 31 | Stairs | Newel not fixed to the structure | High | ☐ |  |  |
| 32 | Stairs | Creak on tread 3 | Medium | ☐ |  |  |
| 33 | Landing | Guarding gap fails the 100 mm sphere check | High | ☐ |  |  |
| 34 | Bedroom 4 | Fitted wardrobe doors not aligned, gaps not consistent | Medium | ☐ |  |  |
| 35 | Bedroom 4 | Wardrobe rail loose | Low | ☐ |  |  |
| 36 | Landing | Loft hatch does not close well | Medium | ☐ |  |  |
| 37 | Kitchen-diner door | Factory-finished door scratched, seen at 0.5 m | Medium | ☐ |  |  |
| 38 | Door to integral garage | Fire door gap over 3 mm | High | ☐ |  |  |
| 39 | Hall door | Internal glazing bead loose | Medium | ☐ |  |  |
| 40 | Stairs | Treads not protected while other trades finish | Medium | ☐ |  |  |
| 41 | Hall | Nail holes not filled before decoration | Low | ☐ |  |  |
| 42 | Kitchen-diner | Room not left clean and ready for decoration | Low | ☐ |  |  |
| 43 |  |  |  | ☐ |  |  |
| 44 |  |  |  | ☐ |  |  |
| 45 |  |  |  | ☐ |  |  |
| 46 |  |  |  | ☐ |  |  |
| 47 |  |  |  | ☐ |  |  |
| 48 |  |  |  | ☐ |  |  |

| Completed by | Checked by | Date |
| --- | --- | --- |