## Snag Sheet
Snag Sheet
Hollins & Reed Contracting Ltd
Project |  | Trade or subcontractor | Issued by |  | Complete by
House extension, House 9 |  | Second-fix joiner | Dan Hollins |  | 2 October 2026
No. | Location | Description of snag | Priority | Done | Date done | Initials
1 | Utility door | Catches at the head and needs force to close | Medium | ☒ | 30/09/26 | PS
2 | WC door | Will not latch | Medium | ☒ | 30/09/26 | PS
3 | Bedroom 4 door | Gap to the jamb over 4 mm | Medium | ☒ | 30/09/26 | PS
4 | Bedroom 4 door | Lining more than 5 mm out of plumb | Medium | ☐
5 | En-suite door | Door distorted more than 5 mm over its height | Medium | ☐
6 | Kitchen-diner door | Gap under the door too small for the floor covering | Medium | ☐
7 | Landing cupboard door | Hinge not flush, screw missing | Medium | ☒ | 30/09/26 | PS
8 | Bedroom 4 door | Door stop not fitted | Low | ☒ | 30/09/26 | PS
9 | Utility door | Handle loose | Medium | ☒ | 30/09/26 | PS
10 | En-suite door | Thumbturn does not engage | High | ☒ | 30/09/26 | PS
11 | Hall door | Architrave reveal not the same on both sides | Low | ☐
12 | Bedroom 4 door | Architrave not parallel to the lining | Low | ☐
13 | Kitchen-diner door | Architrave mitre open at the head | Low | ☐
14 | Landing door | Architrave leg not cut square to the skirting | Low | ☐
15 | Kitchen-diner, window corner | Internal skirting corner mitred and opening up, scribe it | Low | ☐
16 | Hall, wall end | External skirting mitre open | Low | ☐
17 | Kitchen-diner, long wall | Skirting joints not consistent, seen at 2 m in daylight | Low | ☐
18 | Bedroom 4 | Skirting gap to the floor over 5 mm, no covering laid | Medium | ☐
19 | Utility | Skirting loose, gap to the wall | Medium | ☐
20 | Utility, by boiler pipes | Skirting not scribed around the pipe | Low | ☐
21 | Bedroom 4 | Skirting fixed only at the ends and gapping | Medium | ☐
22 | En-suite | Pipe boxing not square | Low | ☐
23 | Bedroom 4 window | Window board not level across its depth | Medium | ☐
24 | Kitchen-diner window | Seal missing at the window board | Low | ☐
Worked example. Change it to fit your job before you use it.
Page 1 of 2
Snag Sheet
Hollins & Reed Contracting Ltd
Project |  | Trade or subcontractor | Issued by |  | Complete by
House extension, House 9 |  | Second-fix joiner | Dan Hollins |  | 2 October 2026
No. | Location | Description of snag | Priority | Done | Date done | Initials
25 | Bedroom 4 window | Window board not scribed to the reveal, gap showing | Low | ☐
26 | Stairs | Handrail loose | High | ☒ | 30/09/26 | PS
27 | Stairs | Handrail fixed to plasterboard alone, fix to the stud | High | ☐
28 | Stairs | Tread 6 loose | High | ☒ | 30/09/26 | PS
29 | Stairs | Gap between tread 2 and the string | Low | ☐
30 | Stairs | Two balusters loose | High | ☒ | 30/09/26 | PS
31 | Stairs | Newel not fixed to the structure | High | ☐
32 | Stairs | Creak on tread 3 | Medium | ☐
33 | Landing | Guarding gap fails the 100 mm sphere check | High | ☐
34 | Bedroom 4 | Fitted wardrobe doors not aligned, gaps not consistent | Medium | ☐
35 | Bedroom 4 | Wardrobe rail loose | Low | ☐
36 | Landing | Loft hatch does not close well | Medium | ☐
37 | Kitchen-diner door | Factory-finished door scratched, seen at 0.5 m | Medium | ☐
38 | Door to integral garage | Fire door gap over 3 mm | High | ☐
39 | Hall door | Internal glazing bead loose | Medium | ☐
40 | Stairs | Treads not protected while other trades finish | Medium | ☐
41 | Hall | Nail holes not filled before decoration | Low | ☐
42 | Kitchen-diner | Room not left clean and ready for decoration | Low | ☐
43 |  |  |  | ☐
44 |  |  |  | ☐
45 |  |  |  | ☐
46 |  |  |  | ☐
47 |  |  |  | ☐
48 |  |  |  | ☐
Completed by |  | Checked by |  | Date
Worked example. Change it to fit your job before you use it.
Page 2 of 2