Snagging List Hollins & Reed Contracting Ltd

| Project Kitchen and bathroom refit, House 4 | Plot or area Kitchen and bathroom | Inspected by Dan Hollins | Date 21 September 2026 |
| --- | --- | --- | --- |

| No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Kitchen, sink | Leak at the waste under the sink | High | Plumber | 21/09/26 | 22/09/26 | ☒ | DH 22/09/26 |
| 2 | Kitchen, sink | Tap drips when turned off | Medium | Plumber | 21/09/26 | 24/09/26 | ☒ | DH 22/09/26 |
| 3 | Kitchen, sink | Sink moves when pressed | Medium | Kitchen fitter | 21/09/26 | 24/09/26 | ☒ | DH 22/09/26 |
| 4 | Kitchen, sink | Seal around the sink cut-out not watertight | High | Kitchen fitter | 21/09/26 | 22/09/26 | ☒ | DH 22/09/26 |
| 5 | Kitchen, sink | Isolation valve cannot be reached | Medium | Plumber | 21/09/26 | 24/09/26 | ☐ |  |
| 6 | Kitchen, wall units | Unit doors out of line, gaps uneven along the run | Medium | Kitchen fitter | 21/09/26 | 24/09/26 | ☐ |  |
| 7 | Kitchen, base unit by cooker | Soft-close door bangs shut | Low | Kitchen fitter | 21/09/26 | 25/09/26 | ☐ |  |
| 8 | Kitchen, pan drawer | Drawer rubs and sits uneven | Medium | Kitchen fitter | 21/09/26 | 24/09/26 | ☐ |  |
| 9 | Kitchen, larder unit | Shelf support missing | Low | Kitchen fitter | 21/09/26 | 25/09/26 | ☐ |  |
| 10 | Kitchen, by fridge | Plinth gapping at the corner | Low | Kitchen fitter | 21/09/26 | 25/09/26 | ☐ |  |
| 11 | Kitchen, worktop by hob | Step at the worktop joint | Medium | Kitchen fitter | 21/09/26 | 24/09/26 | ☐ |  |
| 12 | Kitchen, worktop end | Worktop chipped at the end of the run | Medium | Kitchen fitter | 21/09/26 | 24/09/26 | ☐ |  |
| 13 | Kitchen, behind hob | Silicone to the wall has gaps | Low | Kitchen fitter | 21/09/26 | 25/09/26 | ☐ |  |
| 14 | Kitchen, splashback | Seal at the worktop not neat | Low | Kitchen fitter | 21/09/26 | 25/09/26 | ☐ |  |
| 15 | Kitchen, dishwasher | Panel out of line with the doors beside it | Medium | Kitchen fitter | 21/09/26 | 24/09/26 | ☐ |  |
| 16 | Kitchen, dishwasher | Hose leaks during a cycle | High | Plumber | 21/09/26 | 22/09/26 | ☒ | DH 22/09/26 |

Snagging List Hollins & Reed Contracting Ltd

| Project Kitchen and bathroom refit, House 4 | Plot or area Kitchen and bathroom | Inspected by Dan Hollins | Date 21 September 2026 |
| --- | --- | --- | --- |

| No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 17 | Kitchen, extractor | Noisy, filter not seated | Medium | Kitchen fitter | 21/09/26 | 24/09/26 | ☐ |  |
| 18 | Kitchen, worktop sockets | Socket not where the kitchen plan shows it | Medium | Electrician | 21/09/26 | 24/09/26 | ☐ |  |
| 19 | Kitchen, by hob | Socket not working on a plug-in tester | High | Electrician | 21/09/26 | 22/09/26 | ☒ | DH 22/09/26 |
| 20 | Kitchen, splashback | Faceplates out of line | Low | Electrician | 21/09/26 | 25/09/26 | ☐ |  |
| 21 | Kitchen, wall units | Under-cabinet light not working at the left end | Medium | Electrician | 21/09/26 | 24/09/26 | ☐ |  |
| 22 | Consumer unit | New kitchen circuit not labelled | Medium | Electrician | 21/09/26 | 24/09/26 | ☐ |  |
| 23 | Kitchen, by window | Plaster not neat around the socket | Low | Plasterer | 21/09/26 | 25/09/26 | ☐ |  |
| 24 | Kitchen, walls | Patchy paint around the sockets | Low | Decorator | 21/09/26 | 25/09/26 | ☐ |  |
| 25 | Kitchen, door | Paint on the skirting | Low | Decorator | 21/09/26 | 25/09/26 | ☐ |  |
| 26 | Bathroom, bath | Bath not level | High | Plumber | 21/09/26 | 22/09/26 | ☐ |  |
| 27 | Bathroom, bath | Silicone has gaps, redo with the bath filled | High | Plumber | 21/09/26 | 22/09/26 | ☐ |  |
| 28 | Bathroom, bath | Bath panel loose at the tap end | Medium | Plumber | 21/09/26 | 24/09/26 | ☐ |  |
| 29 | Bathroom, bath | Drains slowly and gurgles | Medium | Plumber | 21/09/26 | 24/09/26 | ☐ |  |
| 30 | Bathroom, shower | Tray flexes underfoot and sounds hollow | High | Plumber | 21/09/26 | 22/09/26 | ☐ |  |
| 31 | Bathroom, shower | Screen not plumb, leaks where it meets the tray | High | Plumber | 21/09/26 | 22/09/26 | ☐ |  |
| 32 | Bathroom, shower | Temperature unstable when the WC is flushed | Medium | Plumber | 21/09/26 | 24/09/26 | ☐ |  |

Snagging List Hollins & Reed Contracting Ltd

| Project Kitchen and bathroom refit, House 4 | Plot or area Kitchen and bathroom | Inspected by Dan Hollins | Date 21 September 2026 |
| --- | --- | --- | --- |

| No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 33 | Bathroom, WC | WC rocks, not sitting flush to the floor | High | Plumber | 21/09/26 | 22/09/26 | ☒ | DH 22/09/26 |
| 34 | Bathroom, WC | Cistern runs on after a flush | Medium | Plumber | 21/09/26 | 24/09/26 | ☐ |  |
| 35 | Bathroom, WC | Flush button sticks | Low | Plumber | 21/09/26 | 25/09/26 | ☐ |  |
| 36 | Bathroom, basin | Basin loose, seal to the wall not complete | Medium | Plumber | 21/09/26 | 24/09/26 | ☐ |  |
| 37 | Bathroom, basin | Chip on the basin edge, seen at 0.5 m | Medium | Plumber | 21/09/26 | 24/09/26 | ☐ |  |
| 38 | Bathroom, behind basin | Hollow-sounding tile | Medium | Tiler | 21/09/26 | 24/09/26 | ☐ |  |
| 39 | Bathroom, window wall | Tile courses not straight | Low | Tiler | 21/09/26 | 25/09/26 | ☐ |  |
| 40 | Bathroom, shower | Pinholes in the grout | Low | Tiler | 21/09/26 | 25/09/26 | ☐ |  |
| 41 | Bathroom, shower valve | Ragged tile cut around the pipes | Low | Tiler | 21/09/26 | 25/09/26 | ☐ |  |
| 42 | Bathroom, towel rail | Tiling not finished behind the pipes | Medium | Tiler | 21/09/26 | 24/09/26 | ☐ |  |
| 43 | Bathroom, ceiling | Extract fan has no overrun | Medium | Electrician | 21/09/26 | 24/09/26 | ☐ |  |
| 44 | Bathroom, towel rail | Cold spot at the top of the rail | Medium | Plumber | 21/09/26 | 24/09/26 | ☐ |  |
| 45 | Bathroom, above basin | Mirror not level | Low | Plumber | 21/09/26 | 25/09/26 | ☐ |  |
| 46 | Bathroom, door | Lock cannot be overridden from outside | Medium | Joiner | 21/09/26 | 24/09/26 | ☐ |  |
| 47 | Bathroom, by door | Floor covering lifting at the edge | Medium | Floor layer | 21/09/26 | 24/09/26 | ☐ |  |

Snagging List Hollins & Reed Contracting Ltd

| Project Kitchen and bathroom refit, House 4 | Plot or area Kitchen and bathroom | Inspected by Dan Hollins | Date 21 September 2026 |
| --- | --- | --- | --- |

| No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 48 | Whole job | Builder’s materials left, final clean not done | Low | Site team | 21/09/26 | 25/09/26 | ☐ |  |
| 49 |  |  |  |  |  |  | ☐ |  |
| 50 |  |  |  |  |  |  | ☐ |  |
| 51 |  |  |  |  |  |  | ☐ |  |
| 52 |  |  |  |  |  |  | ☐ |  |
| 53 |  |  |  |  |  |  | ☐ |  |
| 54 |  |  |  |  |  |  | ☐ |  |
| 55 |  |  |  |  |  |  | ☐ |  |
| 56 |  |  |  |  |  |  | ☐ |  |
| 57 |  |  |  |  |  |  | ☐ |  |
| 58 |  |  |  |  |  |  | ☐ |  |
| 59 |  |  |  |  |  |  | ☐ |  |
| 60 |  |  |  |  |  |  | ☐ |  |
| 61 |  |  |  |  |  |  | ☐ |  |
| 62 |  |  |  |  |  |  | ☐ |  |
| 63 |  |  |  |  |  |  | ☐ |  |