## Snagging List
Snagging List
Hollins & Reed Contracting Ltd
Project |  |  | Plot or area | Inspected by |  | Date
Kitchen and bathroom refit, House 4 |  |  | Kitchen and bathroom | Dan Hollins |  | 21 September 2026
No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off
1 | Kitchen, sink | Leak at the waste under the sink | High | Plumber | 21/09/26 | 22/09/26 | ☒ | DH 22/09/26
2 | Kitchen, sink | Tap drips when turned off | Medium | Plumber | 21/09/26 | 24/09/26 | ☒ | DH 22/09/26
3 | Kitchen, sink | Sink moves when pressed | Medium | Kitchen fitter | 21/09/26 | 24/09/26 | ☒ | DH 22/09/26
4 | Kitchen, sink | Seal around the sink cut-out not watertight | High | Kitchen fitter | 21/09/26 | 22/09/26 | ☒ | DH 22/09/26
5 | Kitchen, sink | Isolation valve cannot be reached | Medium | Plumber | 21/09/26 | 24/09/26 | ☐
6 | Kitchen, wall units | Unit doors out of line, gaps uneven along the run | Medium | Kitchen fitter | 21/09/26 | 24/09/26 | ☐
7 | Kitchen, base unit by cooker | Soft-close door bangs shut | Low | Kitchen fitter | 21/09/26 | 25/09/26 | ☐
8 | Kitchen, pan drawer | Drawer rubs and sits uneven | Medium | Kitchen fitter | 21/09/26 | 24/09/26 | ☐
9 | Kitchen, larder unit | Shelf support missing | Low | Kitchen fitter | 21/09/26 | 25/09/26 | ☐
10 | Kitchen, by fridge | Plinth gapping at the corner | Low | Kitchen fitter | 21/09/26 | 25/09/26 | ☐
11 | Kitchen, worktop by hob | Step at the worktop joint | Medium | Kitchen fitter | 21/09/26 | 24/09/26 | ☐
12 | Kitchen, worktop end | Worktop chipped at the end of the run | Medium | Kitchen fitter | 21/09/26 | 24/09/26 | ☐
13 | Kitchen, behind hob | Silicone to the wall has gaps | Low | Kitchen fitter | 21/09/26 | 25/09/26 | ☐
14 | Kitchen, splashback | Seal at the worktop not neat | Low | Kitchen fitter | 21/09/26 | 25/09/26 | ☐
15 | Kitchen, dishwasher | Panel out of line with the doors beside it | Medium | Kitchen fitter | 21/09/26 | 24/09/26 | ☐
16 | Kitchen, dishwasher | Hose leaks during a cycle | High | Plumber | 21/09/26 | 22/09/26 | ☒ | DH 22/09/26
Worked example. Change it to fit your job before you use it.
Page 1 of 4
Snagging List
Hollins & Reed Contracting Ltd
Project |  |  | Plot or area | Inspected by |  | Date
Kitchen and bathroom refit, House 4 |  |  | Kitchen and bathroom | Dan Hollins |  | 21 September 2026
No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off
17 | Kitchen, extractor | Noisy, filter not seated | Medium | Kitchen fitter | 21/09/26 | 24/09/26 | ☐
18 | Kitchen, worktop sockets | Socket not where the kitchen plan shows it | Medium | Electrician | 21/09/26 | 24/09/26 | ☐
19 | Kitchen, by hob | Socket not working on a plug-in tester | High | Electrician | 21/09/26 | 22/09/26 | ☒ | DH 22/09/26
20 | Kitchen, splashback | Faceplates out of line | Low | Electrician | 21/09/26 | 25/09/26 | ☐
21 | Kitchen, wall units | Under-cabinet light not working at the left end | Medium | Electrician | 21/09/26 | 24/09/26 | ☐
22 | Consumer unit | New kitchen circuit not labelled | Medium | Electrician | 21/09/26 | 24/09/26 | ☐
23 | Kitchen, by window | Plaster not neat around the socket | Low | Plasterer | 21/09/26 | 25/09/26 | ☐
24 | Kitchen, walls | Patchy paint around the sockets | Low | Decorator | 21/09/26 | 25/09/26 | ☐
25 | Kitchen, door | Paint on the skirting | Low | Decorator | 21/09/26 | 25/09/26 | ☐
26 | Bathroom, bath | Bath not level | High | Plumber | 21/09/26 | 22/09/26 | ☐
27 | Bathroom, bath | Silicone has gaps, redo with the bath filled | High | Plumber | 21/09/26 | 22/09/26 | ☐
28 | Bathroom, bath | Bath panel loose at the tap end | Medium | Plumber | 21/09/26 | 24/09/26 | ☐
29 | Bathroom, bath | Drains slowly and gurgles | Medium | Plumber | 21/09/26 | 24/09/26 | ☐
30 | Bathroom, shower | Tray flexes underfoot and sounds hollow | High | Plumber | 21/09/26 | 22/09/26 | ☐
31 | Bathroom, shower | Screen not plumb, leaks where it meets the tray | High | Plumber | 21/09/26 | 22/09/26 | ☐
32 | Bathroom, shower | Temperature unstable when the WC is flushed | Medium | Plumber | 21/09/26 | 24/09/26 | ☐
Worked example. Change it to fit your job before you use it.
Page 2 of 4
Snagging List
Hollins & Reed Contracting Ltd
Project |  |  | Plot or area | Inspected by |  | Date
Kitchen and bathroom refit, House 4 |  |  | Kitchen and bathroom | Dan Hollins |  | 21 September 2026
No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off
33 | Bathroom, WC | WC rocks, not sitting flush to the floor | High | Plumber | 21/09/26 | 22/09/26 | ☒ | DH 22/09/26
34 | Bathroom, WC | Cistern runs on after a flush | Medium | Plumber | 21/09/26 | 24/09/26 | ☐
35 | Bathroom, WC | Flush button sticks | Low | Plumber | 21/09/26 | 25/09/26 | ☐
36 | Bathroom, basin | Basin loose, seal to the wall not complete | Medium | Plumber | 21/09/26 | 24/09/26 | ☐
37 | Bathroom, basin | Chip on the basin edge, seen at 0.5 m | Medium | Plumber | 21/09/26 | 24/09/26 | ☐
38 | Bathroom, behind basin | Hollow-sounding tile | Medium | Tiler | 21/09/26 | 24/09/26 | ☐
39 | Bathroom, window wall | Tile courses not straight | Low | Tiler | 21/09/26 | 25/09/26 | ☐
40 | Bathroom, shower | Pinholes in the grout | Low | Tiler | 21/09/26 | 25/09/26 | ☐
41 | Bathroom, shower valve | Ragged tile cut around the pipes | Low | Tiler | 21/09/26 | 25/09/26 | ☐
42 | Bathroom, towel rail | Tiling not finished behind the pipes | Medium | Tiler | 21/09/26 | 24/09/26 | ☐
43 | Bathroom, ceiling | Extract fan has no overrun | Medium | Electrician | 21/09/26 | 24/09/26 | ☐
44 | Bathroom, towel rail | Cold spot at the top of the rail | Medium | Plumber | 21/09/26 | 24/09/26 | ☐
45 | Bathroom, above basin | Mirror not level | Low | Plumber | 21/09/26 | 25/09/26 | ☐
46 | Bathroom, door | Lock cannot be overridden from outside | Medium | Joiner | 21/09/26 | 24/09/26 | ☐
47 | Bathroom, by door | Floor covering lifting at the edge | Medium | Floor layer | 21/09/26 | 24/09/26 | ☐
Worked example. Change it to fit your job before you use it.
Page 3 of 4
Snagging List
Hollins & Reed Contracting Ltd
Project |  |  | Plot or area | Inspected by |  | Date
Kitchen and bathroom refit, House 4 |  |  | Kitchen and bathroom | Dan Hollins |  | 21 September 2026
No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off
48 | Whole job | Builder’s materials left, final clean not done | Low | Site team | 21/09/26 | 25/09/26 | ☐
49 | [6 empty] | ☐
50 | [6 empty] | ☐
51 | [6 empty] | ☐
52 | [6 empty] | ☐
53 | [6 empty] | ☐
54 | [6 empty] | ☐
55 | [6 empty] | ☐
56 | [6 empty] | ☐
57 | [6 empty] | ☐
58 | [6 empty] | ☐
59 | [6 empty] | ☐
60 | [6 empty] | ☐
61 | [6 empty] | ☐
62 | [6 empty] | ☐
63 | [6 empty] | ☐
Worked example. Change it to fit your job before you use it.
Page 4 of 4