Handover Snagging List Hollins & Reed Contracting Ltd

| Project Office fit-out, Unit 3 | Plot or area First floor | Client Thornley Vale Estates Ltd | Date 9 October 2026 |
| --- | --- | --- | --- |

| No. | Location | Description of snag | Priority | Trade | Date done | Initials | Accepted | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Reception | Paint touch-ups needed beside the entrance door | Low | Decorator | 12/10/26 | DH | ☒ |  |
| 2 | Reception | Manifestation missing on the glazed screen | High | Signage | 12/10/26 | DH | ☒ |  |
| 3 | Reception | Company sign wrong, needs replacing | Medium | Signage |  |  | ☐ | New sign ordered |
| 4 | Reception | Scratch on the glazed screen | Medium | Glazier |  |  | ☐ | Pane to be replaced |
| 5 | Reception | Mastic around the screen frame not complete | Low | Glazier | 12/10/26 | DH | ☒ |  |
| 6 | Reception desk | Joints not tight, cabinet doors not level | Medium | Joiner | 12/10/26 | DH | ☒ |  |
| 7 | Open-plan office, by windows | Two ceiling tiles misaligned | Low | Ceiling fixer | 12/10/26 | DH | ☒ |  |
| 8 | Open-plan office, bay 3 | Ceiling tile damaged | Low | Ceiling fixer | 12/10/26 | DH | ☒ |  |
| 9 | Open-plan office, bay 4 | Carpet seam showing | Medium | Floor layer |  |  | ☐ | Client to view in daylight |
| 10 | Open-plan office, doorway | Floor covering not bonded | Medium | Floor layer | 12/10/26 | DH | ☒ |  |
| 11 | Tea point threshold | Transition strip missing | Medium | Floor layer | 12/10/26 | DH | ☒ |  |
| 12 | Open-plan office, east wall | Skirting not tight to the wall | Low | Joiner | 12/10/26 | DH | ☒ |  |
| 13 | Open-plan office, bay 2 | Lighting sensor not working | Medium | Electrician |  |  | ☐ | Date to be agreed |
| 14 | Meeting room 2 | Lighting control not working | Medium | Electrician | 12/10/26 | DH | ☒ |  |

Handover Snagging List Hollins & Reed Contracting Ltd

| Project Office fit-out, Unit 3 | Plot or area First floor | Client Thornley Vale Estates Ltd | Date 9 October 2026 |
| --- | --- | --- | --- |

| No. | Location | Description of snag | Priority | Trade | Date done | Initials | Accepted | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 15 | Open-plan office, south wall | Sockets set out of square | Low | Electrician | 12/10/26 | DH | ☒ |  |
| 16 | Open-plan office, column C | Socket not working | High | Electrician | 12/10/26 | DH | ☒ |  |
| 17 | Open-plan office, bay 5 | Heating and cooling out of balance | Medium | Mechanical |  |  | ☐ | Not yet tested in full |
| 18 | Meeting room 1 | Door does not latch first time | Medium | Joiner | 12/10/26 | DH | ☒ |  |
| 19 | Meeting room 1 | Handle not fitted | Medium | Joiner | 12/10/26 | DH | ☒ |  |
| 20 | Meeting room 2 | Wall panel joinery out of alignment | Low | Joiner | 12/10/26 | DH | ☒ |  |
| 21 | Meeting room 2 | Paint runs on the door frame | Low | Decorator | 12/10/26 | DH | ☒ |  |
| 22 | Director’s office | Scratch on the factory-finished door, seen at 0.5 m | High | Joiner |  |  | ☐ | Door to be refinished |
| 23 | Director’s office | Sheen varies on the window wall | Medium | Decorator | 12/10/26 | DH | ☒ |  |
| 24 | Director’s office | Timber veneer varies between panels | Low | Joiner |  |  | ☐ | Client to decide |
| 25 | Corridor | Self-closer does not fully close the fire door | High | Joiner | 12/10/26 | DH | ☒ |  |
| 26 | Corridor | Fire door gap over 3 mm | High | Joiner | 12/10/26 | DH | ☒ |  |
| 27 | Corridor | Emergency lighting not tested | High | Electrician |  |  | ☐ | Test booked |
| 28 | Tea point | Worktop joint not tight | Medium | Joiner | 12/10/26 | DH | ☒ |  |
| 29 | Tea point | Grout not finished behind the tap | Low | Tiler | 12/10/26 | DH | ☒ |  |

Handover Snagging List Hollins & Reed Contracting Ltd

| Project Office fit-out, Unit 3 | Plot or area First floor | Client Thornley Vale Estates Ltd | Date 9 October 2026 |
| --- | --- | --- | --- |

| No. | Location | Description of snag | Priority | Trade | Date done | Initials | Accepted | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 30 | Tea point | Silicone not complete at the sink | Low | Tiler | 12/10/26 | DH | ☒ |  |
| 31 | Tea point | Hot water flow not tested at the tap | Medium | Plumber | 12/10/26 | DH | ☒ |  |
| 32 | WCs, cubicle 2 | WC does not operate | High | Plumber | 12/10/26 | DH | ☒ |  |
| 33 | WCs, cubicle 3 | Cubicle lock not working | Medium | Joiner | 12/10/26 | DH | ☒ |  |
| 34 | WCs | Extract fan not working | Medium | Mechanical | 12/10/26 | DH | ☒ |  |
| 35 | Whole floor | Fire alarm not yet certified | High | Fire alarm engineer |  |  | ☐ | Certificate to follow |
| 36 | Whole floor | M&E commissioning not complete | High | Mechanical |  |  | ☐ | Date to be agreed |
| 37 | Whole floor | BMS demonstration not given | Medium | Mechanical |  |  | ☐ | Date to be agreed |
| 38 | Whole floor | Final clean not done | Medium | Cleaner |  |  | ☐ | After the snags are done |
| 39 | Handover documents | O&M manuals not received | High | Site team |  |  | ☐ | Draft received |
| 40 | Handover documents | As-built drawings not issued | High | Site team |  |  | ☐ |  |
| 41 | Handover documents | Test and commissioning certificates not collated | High | Site team |  |  | ☐ |  |
| 42 | Handover documents | Warranties not registered | Medium | Site team |  |  | ☐ |  |
| 43 | Handover documents | Keys and spares not handed over | Medium | Site team |  |  | ☐ |  |

Handover Snagging List Hollins & Reed Contracting Ltd

| Project Office fit-out, Unit 3 | Plot or area First floor | Client Thornley Vale Estates Ltd | Date 9 October 2026 |
| --- | --- | --- | --- |

| No. | Location | Description of snag | Priority | Trade | Date done | Initials | Accepted | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 44 |  |  |  |  |  |  | ☐ |  |
| 45 |  |  |  |  |  |  | ☐ |  |
| 46 |  |  |  |  |  |  | ☐ |  |
| 47 |  |  |  |  |  |  | ☐ |  |
| 48 |  |  |  |  |  |  | ☐ |  |
| 49 |  |  |  |  |  |  | ☐ |  |
| 50 |  |  |  |  |  |  | ☐ |  |
| 51 |  |  |  |  |  |  | ☐ |  |
| 52 |  |  |  |  |  |  | ☐ |  |
| 53 |  |  |  |  |  |  | ☐ |  |
| 54 |  |  |  |  |  |  | ☐ |  |
| 55 |  |  |  |  |  |  | ☐ |  |
| 56 |  |  |  |  |  |  | ☐ |  |
| 57 |  |  |  |  |  |  | ☐ |  |

| For the contractor | For the client | Date |
| --- | --- | --- |