## Handover Snagging List
Handover Snagging List
Hollins & Reed Contracting Ltd
Project |  |  | Plot or area | Client |  |  |  | Date
Office fit-out, Unit 3 |  |  | First floor | Thornley Vale Estates Ltd |  |  |  | 9 October 2026
No. | Location | Description of snag | Priority | Trade | Date done | Initials | Accepted | Comments
1 | Reception | Paint touch-ups needed beside the entrance door | Low | Decorator | 12/10/26 | DH | ☒
2 | Reception | Manifestation missing on the glazed screen | High | Signage | 12/10/26 | DH | ☒
3 | Reception | Company sign wrong, needs replacing | Medium | Signage |  |  | ☐ | New sign ordered
4 | Reception | Scratch on the glazed screen | Medium | Glazier |  |  | ☐ | Pane to be replaced
5 | Reception | Mastic around the screen frame not complete | Low | Glazier | 12/10/26 | DH | ☒
6 | Reception desk | Joints not tight, cabinet doors not level | Medium | Joiner | 12/10/26 | DH | ☒
7 | Open-plan office, by windows | Two ceiling tiles misaligned | Low | Ceiling fixer | 12/10/26 | DH | ☒
8 | Open-plan office, bay 3 | Ceiling tile damaged | Low | Ceiling fixer | 12/10/26 | DH | ☒
9 | Open-plan office, bay 4 | Carpet seam showing | Medium | Floor layer |  |  | ☐ | Client to view in daylight
10 | Open-plan office, doorway | Floor covering not bonded | Medium | Floor layer | 12/10/26 | DH | ☒
11 | Tea point threshold | Transition strip missing | Medium | Floor layer | 12/10/26 | DH | ☒
12 | Open-plan office, east wall | Skirting not tight to the wall | Low | Joiner | 12/10/26 | DH | ☒
13 | Open-plan office, bay 2 | Lighting sensor not working | Medium | Electrician |  |  | ☐ | Date to be agreed
14 | Meeting room 2 | Lighting control not working | Medium | Electrician | 12/10/26 | DH | ☒
Worked example. Change it to fit your job before you use it.
Page 1 of 4
Handover Snagging List
Hollins & Reed Contracting Ltd
Project |  |  | Plot or area | Client |  |  |  | Date
Office fit-out, Unit 3 |  |  | First floor | Thornley Vale Estates Ltd |  |  |  | 9 October 2026
No. | Location | Description of snag | Priority | Trade | Date done | Initials | Accepted | Comments
15 | Open-plan office, south wall | Sockets set out of square | Low | Electrician | 12/10/26 | DH | ☒
16 | Open-plan office, column C | Socket not working | High | Electrician | 12/10/26 | DH | ☒
17 | Open-plan office, bay 5 | Heating and cooling out of balance | Medium | Mechanical |  |  | ☐ | Not yet tested in full
18 | Meeting room 1 | Door does not latch first time | Medium | Joiner | 12/10/26 | DH | ☒
19 | Meeting room 1 | Handle not fitted | Medium | Joiner | 12/10/26 | DH | ☒
20 | Meeting room 2 | Wall panel joinery out of alignment | Low | Joiner | 12/10/26 | DH | ☒
21 | Meeting room 2 | Paint runs on the door frame | Low | Decorator | 12/10/26 | DH | ☒
22 | Director’s office | Scratch on the factory-finished door, seen at 0.5 m | High | Joiner |  |  | ☐ | Door to be refinished
23 | Director’s office | Sheen varies on the window wall | Medium | Decorator | 12/10/26 | DH | ☒
24 | Director’s office | Timber veneer varies between panels | Low | Joiner |  |  | ☐ | Client to decide
25 | Corridor | Self-closer does not fully close the fire door | High | Joiner | 12/10/26 | DH | ☒
26 | Corridor | Fire door gap over 3 mm | High | Joiner | 12/10/26 | DH | ☒
27 | Corridor | Emergency lighting not tested | High | Electrician |  |  | ☐ | Test booked
28 | Tea point | Worktop joint not tight | Medium | Joiner | 12/10/26 | DH | ☒
29 | Tea point | Grout not finished behind the tap | Low | Tiler | 12/10/26 | DH | ☒
Worked example. Change it to fit your job before you use it.
Page 2 of 4
Handover Snagging List
Hollins & Reed Contracting Ltd
Project |  |  | Plot or area | Client |  |  |  | Date
Office fit-out, Unit 3 |  |  | First floor | Thornley Vale Estates Ltd |  |  |  | 9 October 2026
No. | Location | Description of snag | Priority | Trade | Date done | Initials | Accepted | Comments
30 | Tea point | Silicone not complete at the sink | Low | Tiler | 12/10/26 | DH | ☒
31 | Tea point | Hot water flow not tested at the tap | Medium | Plumber | 12/10/26 | DH | ☒
32 | WCs, cubicle 2 | WC does not operate | High | Plumber | 12/10/26 | DH | ☒
33 | WCs, cubicle 3 | Cubicle lock not working | Medium | Joiner | 12/10/26 | DH | ☒
34 | WCs | Extract fan not working | Medium | Mechanical | 12/10/26 | DH | ☒
35 | Whole floor | Fire alarm not yet certified | High | Fire alarm engineer |  |  | ☐ | Certificate to follow
36 | Whole floor | M&E commissioning not complete | High | Mechanical |  |  | ☐ | Date to be agreed
37 | Whole floor | BMS demonstration not given | Medium | Mechanical |  |  | ☐ | Date to be agreed
38 | Whole floor | Final clean not done | Medium | Cleaner |  |  | ☐ | After the snags are done
39 | Handover documents | O&M manuals not received | High | Site team |  |  | ☐ | Draft received
40 | Handover documents | As-built drawings not issued | High | Site team |  |  | ☐
41 | Handover documents | Test and commissioning certificates not collated | High | Site team |  |  | ☐
42 | Handover documents | Warranties not registered | Medium | Site team |  |  | ☐
43 | Handover documents | Keys and spares not handed over | Medium | Site team |  |  | ☐
Worked example. Change it to fit your job before you use it.
Page 3 of 4
Handover Snagging List
Hollins & Reed Contracting Ltd
Project |  |  | Plot or area | Client |  |  |  | Date
Office fit-out, Unit 3 |  |  | First floor | Thornley Vale Estates Ltd |  |  |  | 9 October 2026
No. | Location | Description of snag | Priority | Trade | Date done | Initials | Accepted | Comments
44 | [6 empty] | ☐
45 | [6 empty] | ☐
46 | [6 empty] | ☐
47 | [6 empty] | ☐
48 | [6 empty] | ☐
49 | [6 empty] | ☐
50 | [6 empty] | ☐
51 | [6 empty] | ☐
52 | [6 empty] | ☐
53 | [6 empty] | ☐
54 | [6 empty] | ☐
55 | [6 empty] | ☐
56 | [6 empty] | ☐
57 | [6 empty] | ☐
For the contractor |  |  | For the client |  |  |  | Date
Worked example. Change it to fit your job before you use it.
Page 4 of 4