Snagging List Hollins & Reed Contracting Ltd

| Project New homes, Phase 1 | Plot or area Plot 14 | Inspected by Dan Hollins | Date 5 October 2026 |
| --- | --- | --- | --- |

| No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Lounge, window wall | Wall over 3 mm out under a 2 m straight edge | Medium | Plasterer | 05/10/26 | 08/10/26 | ☐ |  |
| 2 | Hall, stair wall | Over 3 mm out under a 450 mm straight edge | Medium | Plasterer | 05/10/26 | 08/10/26 | ☐ |  |
| 3 | Bedroom 2, ceiling | Over 5 mm out under a 2 m straight edge | Medium | Plasterer | 05/10/26 | 08/10/26 | ☐ |  |
| 4 | Lounge, ceiling | Board joint readily visible at 2 m in daylight | Medium | Plasterer | 05/10/26 | 08/10/26 | ☒ | DH 06/10/26 |
| 5 | Bedroom 1, ceiling | Jointing tape showing | Medium | Plasterer | 05/10/26 | 08/10/26 | ☒ | DH 06/10/26 |
| 6 | Bedroom 3, ceiling | Nail pops along the board edge | Medium | Plasterer | 05/10/26 | 08/10/26 | ☐ |  |
| 7 | Landing, wall | Screw dimples not filled | Low | Plasterer | 05/10/26 | 09/10/26 | ☒ | DH 06/10/26 |
| 8 | Hall, by stairs | Lumps in the plaster, not sanded flat | Low | Plasterer | 05/10/26 | 09/10/26 | ☒ | DH 06/10/26 |
| 9 | Kitchen | Plaster not neat around the sockets | Low | Plasterer | 05/10/26 | 09/10/26 | ☒ | DH 06/10/26 |
| 10 | Bedroom 1, window | Crack near the frame | Medium | Plasterer | 05/10/26 | 08/10/26 | ☐ |  |
| 11 | Lounge, wall to ceiling | Crack at the junction over 2 mm | Medium | Plasterer | 05/10/26 | 08/10/26 | ☐ |  |
| 12 | Bedroom 2, by window | Hollow plaster | Medium | Plasterer | 05/10/26 | 08/10/26 | ☐ |  |
| 13 | Lounge, window | Reveal not plumb | Low | Plasterer | 05/10/26 | 09/10/26 | ☐ |  |
| 14 | Kitchen, by door | Internal corner not neat | Low | Plasterer | 05/10/26 | 09/10/26 | ☐ |  |
| 15 | Bedroom 3, window | Sill out of level | Low | Joiner | 05/10/26 | 09/10/26 | ☐ |  |
| 16 | Lounge | Coving joint open over 2 mm | Low | Plasterer | 05/10/26 | 09/10/26 | ☐ |  |

Snagging List Hollins & Reed Contracting Ltd

| Project New homes, Phase 1 | Plot or area Plot 14 | Inspected by Dan Hollins | Date 5 October 2026 |
| --- | --- | --- | --- |

| No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 17 | Bathroom, wall | Damp patch, find the cause first | High | Plumber | 05/10/26 | 06/10/26 | ☐ |  |
| 18 | Landing, ceiling | Stain on the ceiling, fix the cause first | High | Plumber | 05/10/26 | 06/10/26 | ☐ |  |
| 19 | Lounge, window wall | Paint coverage thin | Medium | Decorator | 05/10/26 | 08/10/26 | ☐ |  |
| 20 | Hall, walls | Sheen varies at normal viewing distance | Medium | Decorator | 05/10/26 | 08/10/26 | ☐ |  |
| 21 | Bedroom 1, walls | Streaks in the paint | Medium | Decorator | 05/10/26 | 08/10/26 | ☐ |  |
| 22 | Landing, door frame | Paint runs | Low | Decorator | 05/10/26 | 09/10/26 | ☐ |  |
| 23 | Bedroom 2, behind door | Missed area | Medium | Decorator | 05/10/26 | 08/10/26 | ☒ | DH 06/10/26 |
| 24 | Kitchen, floor | Paint splashes | Low | Decorator | 05/10/26 | 09/10/26 | ☒ | DH 06/10/26 |
| 25 | Bedroom 3, window | Paint splash on the glass | Low | Decorator | 05/10/26 | 09/10/26 | ☒ | DH 06/10/26 |
| 26 | Lounge, radiator | Decoration not finished behind the radiator | Low | Decorator | 05/10/26 | 09/10/26 | ☐ |  |
| 27 | Bedroom 2, cupboard | Inside not decorated as specified | Medium | Decorator | 05/10/26 | 08/10/26 | ☐ |  |
| 28 | Kitchen, walls | Patchy around the sockets | Low | Decorator | 05/10/26 | 09/10/26 | ☐ |  |
| 29 | Hall | Paint on the skirting | Low | Decorator | 05/10/26 | 09/10/26 | ☒ | DH 06/10/26 |
| 30 | Stairs, woodwork | Nail holes and splits not filled | Low | Decorator | 05/10/26 | 09/10/26 | ☐ |  |
| 31 | Bedroom 1 | Colour not consistent between two walls | Medium | Decorator | 05/10/26 | 08/10/26 | ☐ |  |
| 32 | Hall, skirting | Joins between lengths open | Low | Decorator | 05/10/26 | 09/10/26 | ☐ |  |

Snagging List Hollins & Reed Contracting Ltd

| Project New homes, Phase 1 | Plot or area Plot 14 | Inspected by Dan Hollins | Date 5 October 2026 |
| --- | --- | --- | --- |

| No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 33 | Lounge, window | Gaps around the frame not caulked | Low | Decorator | 05/10/26 | 09/10/26 | ☐ |  |
| 34 | WC, walls | Plasterboard showing through thin paint | Medium | Decorator | 05/10/26 | 08/10/26 | ☐ |  |
| 35 | Bedroom 3, door | Undercoat showing through the top coat | Medium | Decorator | 05/10/26 | 08/10/26 | ☐ |  |
| 36 | Landing, walls | Rough, gritty paint finish | Low | Decorator | 05/10/26 | 09/10/26 | ☐ |  |
| 37 | Hall, door frame | Knot bleeding through the paint | Low | Decorator | 05/10/26 | 09/10/26 | ☐ |  |
| 38 | Hall, walls | Scuffed by other trades, touch up | Low | Decorator | 05/10/26 | 09/10/26 | ☐ |  |
| 39 | Bathroom, ceiling | Black mould on the ceiling, check the extract fan first | High | Electrician | 05/10/26 | 06/10/26 | ☐ |  |
| 40 | Front door | External decoration not complete | Medium | Decorator | 05/10/26 | 08/10/26 | ☐ |  |
| 41 |  |  |  |  |  |  | ☐ |  |
| 42 |  |  |  |  |  |  | ☐ |  |
| 43 |  |  |  |  |  |  | ☐ |  |
| 44 |  |  |  |  |  |  | ☐ |  |
| 45 |  |  |  |  |  |  | ☐ |  |
| 46 |  |  |  |  |  |  | ☐ |  |
| 47 |  |  |  |  |  |  | ☐ |  |
| 48 |  |  |  |  |  |  | ☐ |  |