## Snagging List
Snagging List
Hollins & Reed Contracting Ltd
Project |  |  | Plot or area | Inspected by |  | Date
New homes, Phase 1 |  |  | Plot 14 | Dan Hollins |  | 5 October 2026
No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off
1 | Lounge, window wall | Wall over 3 mm out under a 2 m straight edge | Medium | Plasterer | 05/10/26 | 08/10/26 | ☐
2 | Hall, stair wall | Over 3 mm out under a 450 mm straight edge | Medium | Plasterer | 05/10/26 | 08/10/26 | ☐
3 | Bedroom 2, ceiling | Over 5 mm out under a 2 m straight edge | Medium | Plasterer | 05/10/26 | 08/10/26 | ☐
4 | Lounge, ceiling | Board joint readily visible at 2 m in daylight | Medium | Plasterer | 05/10/26 | 08/10/26 | ☒ | DH 06/10/26
5 | Bedroom 1, ceiling | Jointing tape showing | Medium | Plasterer | 05/10/26 | 08/10/26 | ☒ | DH 06/10/26
6 | Bedroom 3, ceiling | Nail pops along the board edge | Medium | Plasterer | 05/10/26 | 08/10/26 | ☐
7 | Landing, wall | Screw dimples not filled | Low | Plasterer | 05/10/26 | 09/10/26 | ☒ | DH 06/10/26
8 | Hall, by stairs | Lumps in the plaster, not sanded flat | Low | Plasterer | 05/10/26 | 09/10/26 | ☒ | DH 06/10/26
9 | Kitchen | Plaster not neat around the sockets | Low | Plasterer | 05/10/26 | 09/10/26 | ☒ | DH 06/10/26
10 | Bedroom 1, window | Crack near the frame | Medium | Plasterer | 05/10/26 | 08/10/26 | ☐
11 | Lounge, wall to ceiling | Crack at the junction over 2 mm | Medium | Plasterer | 05/10/26 | 08/10/26 | ☐
12 | Bedroom 2, by window | Hollow plaster | Medium | Plasterer | 05/10/26 | 08/10/26 | ☐
13 | Lounge, window | Reveal not plumb | Low | Plasterer | 05/10/26 | 09/10/26 | ☐
14 | Kitchen, by door | Internal corner not neat | Low | Plasterer | 05/10/26 | 09/10/26 | ☐
15 | Bedroom 3, window | Sill out of level | Low | Joiner | 05/10/26 | 09/10/26 | ☐
16 | Lounge | Coving joint open over 2 mm | Low | Plasterer | 05/10/26 | 09/10/26 | ☐
Worked example. Change it to fit your job before you use it.
Page 1 of 3
Snagging List
Hollins & Reed Contracting Ltd
Project |  |  | Plot or area | Inspected by |  | Date
New homes, Phase 1 |  |  | Plot 14 | Dan Hollins |  | 5 October 2026
No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off
17 | Bathroom, wall | Damp patch, find the cause first | High | Plumber | 05/10/26 | 06/10/26 | ☐
18 | Landing, ceiling | Stain on the ceiling, fix the cause first | High | Plumber | 05/10/26 | 06/10/26 | ☐
19 | Lounge, window wall | Paint coverage thin | Medium | Decorator | 05/10/26 | 08/10/26 | ☐
20 | Hall, walls | Sheen varies at normal viewing distance | Medium | Decorator | 05/10/26 | 08/10/26 | ☐
21 | Bedroom 1, walls | Streaks in the paint | Medium | Decorator | 05/10/26 | 08/10/26 | ☐
22 | Landing, door frame | Paint runs | Low | Decorator | 05/10/26 | 09/10/26 | ☐
23 | Bedroom 2, behind door | Missed area | Medium | Decorator | 05/10/26 | 08/10/26 | ☒ | DH 06/10/26
24 | Kitchen, floor | Paint splashes | Low | Decorator | 05/10/26 | 09/10/26 | ☒ | DH 06/10/26
25 | Bedroom 3, window | Paint splash on the glass | Low | Decorator | 05/10/26 | 09/10/26 | ☒ | DH 06/10/26
26 | Lounge, radiator | Decoration not finished behind the radiator | Low | Decorator | 05/10/26 | 09/10/26 | ☐
27 | Bedroom 2, cupboard | Inside not decorated as specified | Medium | Decorator | 05/10/26 | 08/10/26 | ☐
28 | Kitchen, walls | Patchy around the sockets | Low | Decorator | 05/10/26 | 09/10/26 | ☐
29 | Hall | Paint on the skirting | Low | Decorator | 05/10/26 | 09/10/26 | ☒ | DH 06/10/26
30 | Stairs, woodwork | Nail holes and splits not filled | Low | Decorator | 05/10/26 | 09/10/26 | ☐
31 | Bedroom 1 | Colour not consistent between two walls | Medium | Decorator | 05/10/26 | 08/10/26 | ☐
32 | Hall, skirting | Joins between lengths open | Low | Decorator | 05/10/26 | 09/10/26 | ☐
Worked example. Change it to fit your job before you use it.
Page 2 of 3
Snagging List
Hollins & Reed Contracting Ltd
Project |  |  | Plot or area | Inspected by |  | Date
New homes, Phase 1 |  |  | Plot 14 | Dan Hollins |  | 5 October 2026
No. | Location | Description of snag | Priority | Trade | Date raised | Due | Done | Signed off
33 | Lounge, window | Gaps around the frame not caulked | Low | Decorator | 05/10/26 | 09/10/26 | ☐
34 | WC, walls | Plasterboard showing through thin paint | Medium | Decorator | 05/10/26 | 08/10/26 | ☐
35 | Bedroom 3, door | Undercoat showing through the top coat | Medium | Decorator | 05/10/26 | 08/10/26 | ☐
36 | Landing, walls | Rough, gritty paint finish | Low | Decorator | 05/10/26 | 09/10/26 | ☐
37 | Hall, door frame | Knot bleeding through the paint | Low | Decorator | 05/10/26 | 09/10/26 | ☐
38 | Hall, walls | Scuffed by other trades, touch up | Low | Decorator | 05/10/26 | 09/10/26 | ☐
39 | Bathroom, ceiling | Black mould on the ceiling, check the extract fan first | High | Electrician | 05/10/26 | 06/10/26 | ☐
40 | Front door | External decoration not complete | Medium | Decorator | 05/10/26 | 08/10/26 | ☐
41 | [6 empty] | ☐
42 | [6 empty] | ☐
43 | [6 empty] | ☐
44 | [6 empty] | ☐
45 | [6 empty] | ☐
46 | [6 empty] | ☐
47 | [6 empty] | ☐
48 | [6 empty] | ☐
Worked example. Change it to fit your job before you use it.
Page 3 of 3